## ProductBackLog
Project Name: Vaccine Integrity Monitoring System (VIMS) Group Members: Muhammet Ali ÖKAN / Ceren ACAY / Azra AKGÜN / Emir Taha GÖKÇE / Ömer Talha ÇEKMEZ / Kayra Alp UŞAKLI / Hakkı Can DURAN / Ege ENGİN
# | Product BackLog
1 | QR Code Reading Infrastructure: Development of QR code scanning capability using handheld terminals or mobile devices at shipping points.
2 | Sensor Data Collection Module: Writing the necessary services to retrieve temperature, humidity, and motion data from sensors at specified intervals.
3 | Real-Time Data Transmission: Establishing the network layer that enables the instantaneous transfer of collected sensor data to the central location.
4 | Smart Storage Container Integration: Retrieval of environmental data from smart vaccine transport bags via API.
5 | Threshold-Based Alert and Notification System: The system shall automatically detect temperature values outside the predefined safe range and notify supervisors through email and mobile application in case of temperature deviations or connection losses.
6 | Forecasting Algorithm: Creation of an artificial intelligence/analytics model that predicts potential cold chain disruptions by analyzing environmental trends.
7 | Intelligent Route and ETA Analytics: Development of a smart tracking module that calculates dynamic estimated delivery times based on live location and historical data, while automatically detecting and alerting supervisors to any significant route deviations or unplanned delays.
8 | Live Tracking Panel: An interface design where authorized users can instantly monitor the shipment location and status on a map.
9 | Digital Arrival Report Generation: Creation of a comprehensive report at the end of the shipment containing temperature logs, humidity levels, and location data.
10 | Data Archiving System: Configuration of the database architecture where all shipment and sensor data will be securely and accessibly stored for 5 years.
11 | TLS Encryption Protocol: Implementation of TLS encryption for all traffic to ensure data transmission security.
12 | Authentication and Authorization: Development of a role-based login mechanism that restricts access to the system.
13 | Performance Optimization: Speed optimization to ensure that sensor data is processed and displayed within 5 seconds after reaching the system
14 | High Availability Configuration: Server infrastructure to ensure 99% uninterrupted system operation during active deliveries.
15 | Data Integrity and Logging: Ensuring the immutability of sensor data in the database and maintaining a history of potential changes.
16 | Automatic Reconnection Mechanism: Adding the "auto-reconnect" feature, which enables the system to reconnect within 30 seconds in case of network loss
17 | UX Improvement : Interface navigation arrangement that enables users to access shipment status in maximum 3 clicks
18 | Scalability Tests: Testing the system's capability to monitor 10,000 shipments simultaneously and load balancing settings.
19 | Seamless Update Infrastructure: Establishing an architecture that enables system updates without interrupting the monitoring service.

## Sprint-1
SPRINT-1
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer, Product Owner | Data Archiving System | In Progress | High | 2026-03-30 | 2026-04-06 | 6 | Configuration of the database architecture where all shipment and sensor data will be securely and accessibly stored for 5 years.
Developer | UX Design | Ready to Start | Low | 2026-04-01 | 2026-04-06 | 4 | Interface navigation arrangement that enables users to access shipment status in maximum 3 clicks.
Developer | Authentication and Authorization | Ready to Start | High | 2026-04-07 | 2026-04-09 | 3 | Development of a role-based login mechanism that restricts access to the system.
Developer | Sensor Data Collection Module | Ready to Start | High | 2026-04-08 | 2026-04-13 | 4 | Writing the necessary services to retrieve temperature, humidity, and motion data from sensors at specified intervals.
Developer | Smart Storage Container Integration | Ready to Start | High | 2026-04-09 | 2026-04-13 | 3 | Retrieval of environmental data from smart vaccine transport bags via API.
11
BACKLOG
As a customer, I want my data to be stored securely in the system so that I can access historical data whenever needed.
STATUS: Ready to Start
As a customer, I want only authorized users to access the system so that unauthorized usage is prevented.
STATUS: Ready to Start
Dev
Dev

## Sprint-2
SPRINT-2
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer | Real-Time Data Transmission | Not Started | High | 2026-04-14 | 2026-04-17 | 4 | Establishing the network layer that enables the instantaneous transfer of collected sensor data to the central location.
Developer | Automatic Reconnection Mechanism | Not Started | High | 2026-04-20 | 2026-04-22 | 3 | Adding the "auto-reconnect" feature, which enables the system to reconnect within 30 seconds in case of network loss.
Developer | Data Integrity and Logging | Not Started | High | 2026-04-20 | 2026-04-24 | 5 | Ensuring the immutability of sensor data in the database and maintaining a history of potential changes.
Developer | Threshold-Based Alert and Notification System | Not Started | High | 2026-04-27 | 2026-04-27 | 1 | The system shall automatically detect temperature values outside the predefined safe range and notify supervisors through email and mobile application in case of temperature deviations or connection losses.
10
BACKLOG
As a customer, I want sensor data to be transmitted in real-time so that I can continuously monitor conditions without delays.
STATUS: Not Started
As a customer, I want to receive alerts and notifications when abnormal conditions or system issues occur so that I can take immediate action..
STATUS: Not Started
Dev
As a customer, I want data transmission to be reliable with automatic reconnection in case of network issues so that I do not lose critical data.
STATUS: Not Started
Dev
Dev

## Sprint-3
SPRINT-3
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer | QR Code Reading Infrastructure | Not Started | Medium | 2026-04-29 | 2026-05-01 | 3 | Development of QR code scanning capability using handheld terminals or mobile devices at shipping points
Developer | Live Tracking Panel | Not Started | Medium | 2026-04-29 | 2026-04-30 | 2 | An interface design where authorized users can instantly monitor the shipment location and status on a map
Developer | AI-Powered Predictive & Logistics Analytics | Not Started | Medium | 2026-05-01 | 2026-05-06 | 4 | Creation of an AI model that predicts potential cold chain disruptions by analyzing environmental trends, while calculating dynamic ETAs and automatically alerting supervisors to any significant route deviations or unplanned delays.
Developer | Availability Configuration | Not Started | Medium | 2026-04-30 | 2026-05-12 | 9 | Server infrastructure to ensure 99% uninterrupted system operation during active deliveries
10
BACKLOG
As a customer, I want to track my shipments in real-time with QR code support and a live tracking interface so that I can instantly monitor their location and status.
STATUS: Not Started
As a customer, I want the system to provide intelligent predictions, route optimization, and high availability so that I can anticipate potential issues, receive accurate delivery estimates, and ensure uninterrupted service.
STATUS: Not Started
Dev
Dev

## Sprint-4
SPRINT-4
STAFF | ACTION | STATUS | PRIORITY | START | FINISH | DURATION (DAYS) | NOTES AND COMMENTS
Developer | Scalability Tests | Not Started | High | 2026-05-14 | 2026-05-20 | 5 | Testing the system's capability to monitor 10,000 shipments simultaneously and load balancing settings.
Developer | Seamless Update Infrastructure | Not Started | Medium | 2026-05-14 | 2026-05-19 | 4 | Establishing an architecture that enables system updates without interrupting the monitoring service.
Developer | Performance Optimization | Not Started | Low | 2026-05-21 | 2026-05-25 | 3 | Speed optimization to ensure that sensor data is processed and displayed within 5 seconds after reaching the system.
Developer | Digital Arrival Report Generation | Not Started | Low | 2026-05-18 | 2026-05-22 | 5 | Creation of a comprehensive report at the end of the shipment containing temperature logs, humidity levels, and location data.
Developer | TLS Encryption Protocol | Not Started | High | 2026-05-18 | 2026-05-19 | 2 | Implementation of TLS encryption for all traffic to ensure data transmission security.
8
BACKLOG
As an operations manager, I want the system to handle thousands of shipments simultaneously and process data within a maximum of 5 seconds, so that I can manage operations without delays even under heavy load.
STATUS: Not Started
As a system administrator, I want system updates to be performed without service interruption, so that the monitoring process can continue without any downtime.
STATUS: Not Started
Dev
Dev
As a user, I want to easily access a detailed report containing temperature, humidity, and location data at the end of each shipment, and navigate the system within a maximum of 3 clicks, so that I can analyze the process quickly and efficiently.
STATUS: Not Started
Dev

## KeyDropdowns
KEY DROPDOWNS - DO NOT DELETE
PRIORITY KEY | STATUS KEY
High | In Progress
Medium | Ready to Start
Low | Complete
On Hold
Testing
Not Started

## Templates
TEMPLATES
ASSIGNED TO | KANBAN CARDS
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
XX
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here
As a [role], I want [goal], so that [benefit]
STATUS: Note Status Here